## Sheet1
PROJECT REPORT
GROUP 1
WEEK 1(9/5/2022-15/5/52022)
I. Team Contribution
# | Project Task | Member | Notes(Task Details,etc,...) |  | ¦ Quy tắc nhóm ¦
1 | Choose topic project | All | Online Clothes&Shoes Shop System |  | 1 . Tất cả mọi người trong nhóm đều phải tự code front - end , back - end của màn hình được giao .
2 | Find out user classes,user cases and function requirements | Trần Thi Tuyết Lan |  |  | 2. Chỉ có technical Leadder . làm tài liệu phần chung là file Backlog , Weekly Meeting , vạch ra khung chương trình của nhóm
|  | Lê Thị Vân Anh |  |  | 3. Chi có TL design databasse table diagram ( 20-25 tables )
3 | Design database | Bùi Quốc Vũ | Database design including data types |  | 4 . Mọi thành viên 1 ngày code 2 giờ , viết docs 30 phút , họp nhóm hàng ngày 10 phút .
|  | Đỗ Đức Hữu |  |  | 5. Ai không code được thì kêu lên với nhóm , nhóm cùng giúp đỡ để code dc . Phải ghi vấn đề gặp phải đê nêu ra phương hướng giải quyết.
Bùi Thái Dương
4 | Find templates and Screens Flow | Phạm Anh Đức
II. Next Week(16/5/2022-22/5/2022)
# | Project Work Item | Time | Notes(Task Details,etc,...) | Link Google Meet
1 | Skills Training | 16h-17h30(17/5/2022) | HTML, CSS, JS | https://meet.google.com/thy-kwdy-mdf?authuser=0
2 | SRS documents & unified screen flow&database | 14h30-16h(19/5/2022) |  | https://meet.google.com/thy-kwdy-mdf?authuser=0
3 | Skills Training | 16h20-17h30(19/5/2022) | JSP,Servlet | https://meet.google.com/thy-kwdy-mdf?authuser=0
4 | Code 6 first screen |  | JSP,Servlet | https://meet.google.com/thy-kwdy-mdf?authuser=0