## Cover
PROJECT REPORT
GROUP 1
This is a work status report for the week, and identifies plans and goals for the following weeks.
The report is summarized at the end of each week and will be updated in the future.
Members:
+ Trần Văn Đức (Leader- ductvhe141699);
+ Ngô Thị Ngọc Mai (maintnhe151402);
+ Nguyễn Duy Mạnh (MANHNDHE141170);
+ Bạch Ngọc Minh Châu(CHAUBNMHE153019);
+ Nguyễn Gia Phú (PHUNGHE150108);
+ Đinh Tiến Lâm(lamdthe153097).

## Week 3
Time: | 20/09/2021 - 24/09/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details) |  | ¦ Quy tắc nhóm ¦
1 | Database | Completed | Ready for the project |  | 1 . Tất cả mọi người trong nhóm đều phải tự code front - end , back - end của màn hình được giao .
2 | Created working environment in Github for group | Completed | Completed |  | 2. Chỉ có technical Leadder . làm tài liệu phần chung là file Backlog , Weekly Meeting , vạch ra khung chương trình của nhóm
3. Chi có TL design databasse table diagram ( 20-25 tables )
II. Team Contribution |  |  |  |  | 4 . Mọi thành viên 1 ngày code 2 giờ , viết docs 30 phút , họp nhóm hàng ngày 10 phút .
# | Project Task | Member | Notes (Task Details, etc.) |  | 5. Ai không code được thì kêu lên với nhóm , nhóm cùng giúp đỡ để code dc . Phải ghi vấn đề gặp phải đê nêu ra phương hướng giải quyết.
1 | Complete the Architecture Design section | Bùi Quốc Vũ & Bùi Thái Dương | none
2 | Update ProductBackLog&SRS Documents&Weekly Report for Week 3 | All Member | none
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | When creating an account on Github, some of you did not register under gmail @fpt.edu.vn or set up an illegal name. | Completed | problem solved
IV. Next Week Plan
# | Project Work Item | Time | Notes (Task Details, etc.) | Link Google Meet | Mentor
1 | Javascript | 21h - 22h30 (28/09/2021) | Some concepts and some simple syntax | link | Bùi Quốc Vũ
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | none
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C15: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue