## BackLog
THE APPLICATION DEVELOPMENT PROJECT TOPIC (SWP391)
ASSIGNMENT FUNCTION DETAILS - ONLINE SHOPPING SYSTEM
ITERATION 1 BACKLOG
Project: Online Shop
# | Feature | Function/Screen Details | Iteration | Level | LOC | In Charge | Status | Estimate
1 | Home Page | It allow everyone can view and search product in website | Iteration 1 | Medium | 120 | Lê Thị Vân Anh | Pending
2 | Product List | Customer can see products that they have just searched | Iteration 1 | Complex | 240 | Bùi Thái Dương | Completed
3 | Product Details | Details like description, color, size, ... for customer to choose | Iteration 1 | Medium | 120 | Bùi Thái Dương | Completed
4 | Cart Details | List of all the products that have been added into the cart | Iteration 1 | Medium | 120 |  | Completed
5 | User Login | User will login with account | Iteration 1 | Common | 60 | Lê Thị Vân Anh | Completed
6 | User Register | Customer can register a new account here | Iteration 1 | Common | 60 | Phạm Anh Đức | Completed