## Cover
PROJECT REPORT
GROUP 1
This is a work status report for the week, and identifies plans and goals for the following weeks.
The report is summarized at the end of each week and will be updated in the future.
Members:
+ Trần Văn Đức (Leader- ductvhe141699);
+ Ngô Thị Ngọc Mai (maintnhe151402);
+ Nguyễn Duy Mạnh (MANHNDHE141170);
+ Bạch Ngọc Minh Châu(CHAUBNMHE153019);
+ Nguyễn Gia Phú (PHUNGHE150108);
+ Đinh Tiến Lâm(lamdthe153097).

## Week 2
Time: | 13/09/2021 - 17/09/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS Document | Completed | The specification document is complete, and the documentation is subject to change during the design and implementation of the software system development.
2 | Screen Layout | Completed | The layout is sketchy and references from other websites. More information can be found in the attached specification document
3 | Database | In Progress | Completed diagram, but no data to use yet
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Database Diagram | Bùi Quốc Vũ | Completed
2 | screen layout design | Lê Thị Vân Anh | Screen: Home Page & Product Details & Cart Details & User Login & User Register
3 | screen layout design | Phạm Anh Đức | Screen: Cart Completion & Reset Password & Change Password & User Profile
4 | screen layout design | Đỗ Đức Hữu | Screen: My Orders & Order Information & Products List [Sale] & Orders List [Admin]
5 | screen layout design | Bùi Quốc Vũ | Screen: Order Details [Sale] & Feedback & Blogs List & Blog Details
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Cac thanh vien chua hieu ro van de | Pending | Se tao mot cuoc hop de giai thich lai toan bo
2 | Cau truc thu muc cua 1 so thanh vien chua duoc ro rang | Pending | Se tao mot cuoc hop de giai thich lai toan bo & yeu cau cac thanh vien bao cao lai tinh hinh
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Temporarily only plan to start coding next week
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | None
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C19: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue