## BackLog
THE APPLICATION DEVELOPMENT PROJECT TOPIC (SWP391)
ASSIGNMENT FUNCTION DETAILS - ONLINE SHOPPING SYSTEM
ITERATION 1 BACKLOG
Project: Online Shop
# | Feature | Function/Screen Details | Iteration | Level | LOC | In Charge | Status | Note
1 | Home Page | It allow everyone can view and search product in website | Iteration 1 | Medium | 120 | Lê Thị Vân Anh | Pending
2 | Product List | Customer can see products that they have just searched | Iteration 1 | Complex | 240 | Bùi Thái Dương | Pending
3 | Product Details | Details like description, color, size, ... for customer to choose | Iteration 1 | Medium | 120 | Bùi Thái Dương | Pending
4 | Cart Details | List of all the products that have been added into the cart | Iteration 1 | Medium | 120 | Bùi Quốc Vũ | Completed
5 | User Login | User will login with account | Iteration 1 | Common | 60 | Lê Thị Vân Anh | Completed
6 | User Register | Customer can register a new account here | Iteration 1 | Common | 60 | Phạm Anh Đức | Completed
7 | User Profile | Customer can register view their infomation | Iteration 1 | Medium | 120 | Đỗ Đức Hữu | Completed
8 | User List | Admin manage accounts | Iteration 1 | Simple | 120 | Phạm Anh Đức | Completed