## Iteration 1
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 1 BACKLOG
# | Function/Screen | Level* | LOC | In Charge | Status | Notes
1 | User Login | Simple | 60 | Lê Thị Vân Anh | Done
2 | User Register | Simple | 60 | Bùi Thái Dương | Done
3 | User Authorization | Complex | 240 | Bùi Thái Dương | Done
4 | Blogs List | Medium | 120 | Bùi Quốc Vũ | Done
5 | Blog Details | Simple | 60 | Bùi Quốc Vũ | Done
6 | Posts List | Medium | 120 | Phạm Anh Đức | Done
7 | Post Details | Medium | 120 | Đỗ Đức Hữu | Done
8 | User List | Simple | 60 | Phạm Anh Đức | Done

## Iteration 2
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 2 BACKLOG
# | Function/Screen | Level* | LOC | In Charge | Status | Notes
9 | Customers List[Seller] | Simple | 60 | Lê Thị Vân Anh | Done
10 | Cart Completion (Place Order) | Complex | 240 | Bùi Thái Dương | Done
11 | Reset Password | Medium | 120 | Trần Thị Tuyết Lan | Done
12 | Change Password | Simple | 60 | Đỗ Đức Hữu | Done
13 | User Profile | Simple | 60 | Lê Thị Vân Anh | Done
14 | My Orders (xem lịch sử order) (Tổng quát) | Simple | 60 | Phạm Anh Đức | Done

## Iteration 3
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 3 BACKLOG
# | Function/Screen | Level* | LOC | In Charge | Status | Notes
15 | Order Information | Medium | 120 | Bùi Thái Dương | Done
16 | Products List [Sale] | Medium | 120 | Bùi Thái Dương | Done
17 | Orders List [Sale] | Simple | 60 | Trần Thị Tuyết Lan | Done
18 | Order Details [Sale] | Simple | 60 | Phạm Anh Đức | Done
19 | Feedback | Simple | 60 | Lê Thị Vân Anh | Done
20 | Blogs List | Medium | 120 | Bùi Quốc Vũ | Done
21 | Add Blog | Simple | 60 | Bùi Quốc Vũ | Done
22 | Update Blog | Simple | 60 | Bùi Quốc Vũ | Done
23 | Blog Details | Simple | 60 | Bùi Quốc Vũ | Done
24 | Notification | Medium | 120 | Bùi Thái Dương | Done
25 | Dashboard | Medium | 120 | Bùi Thái Dương | Done
26 | About Shop | Simple | 60 | Phạm Anh Đức | Done
27 | Blog Management | Medium | 120 | Bùi Quốc Vũ | Done

## Iteration 4
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 4 BACKLOG
# | Function/Screen | Level* | LOC | In Charge | Status | Notes
28 | Error | Simple | 60 | Bùi Quốc Vũ | Done
29 | About Shope | Simple | 60 | Bùi Quốc Vũ | Done
30 | Authoriation | Complex | 240 | Bùi Thái Dương | Done
31 | Shipping | Simple | 60 | Bùi Thái Dương | Done
32 | Dashboard | Simple | 60 | Bùi Thái Dương | Done
33 | Manager Feedback [Seller] | Simple | 60 | Phạm Anh Đức | Done
34 | Manager Feedback [Customer] | Simple | 60 | Phạm Anh Đức | Done
35 | Manager banner | Simple | 60 | Đỗ Đức Hữu | Done