## Cover
PROJECT REPORT
GROUP 1
This is a work status report for the week, and identifies plans and goals for the following weeks.
The report is summarized at the end of each week and will be updated in the future.
Members:
+ Trần Văn Đức (Leader- ductvhe141699);
+ Ngô Thị Ngọc Mai (maintnhe151402);
+ Nguyễn Duy Mạnh (MANHNDHE141170);
+ Bạch Ngọc Minh Châu(CHAUBNMHE153019);
+ Nguyễn Gia Phú (PHUNGHE150108);
+ Đinh Tiến Lâm(lamdthe153097).

## Week 3
Time: | 6/6/2022 - 12/6/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details) |  | ¦ Quy tắc nhóm ¦
1 | Continue implementing Iteration 1 | In Progress | The interface of each member is not uniform in terms of layout, color,... The BackEnd only completed three out of six screens (50%) |  | 1 . Tất cả mọi người trong nhóm đều phải tự code front - end , back - end của màn hình được giao .
2 | Start implementating Iteration 2 | In Progress | none |  | 2. Chỉ có technical Leadder . làm tài liệu phần chung là file Backlog , Weekly Meeting , vạch ra khung chương trình của nhóm
3. Chi có TL design databasse table diagram ( 20-25 tables )
II. Team Contribution |  |  |  |  | 4 . Mọi thành viên 1 ngày code 2 giờ , viết docs 30 phút , họp nhóm hàng ngày 10 phút .
# | Project Task | Member | Notes (Task Details, etc.) |  | 5. Ai không code được thì kêu lên với nhóm , nhóm cùng giúp đỡ để code dc . Phải ghi vấn đề gặp phải đê nêu ra phương hướng giải quyết.
1 | Cart Details & Cart Completion (Place Order) | Bùi Thái Dương | Complete
2 | Orders List [Sale] + Sale DashBoard | Đỗ Đức Hữu& Lê Thị Vân Anh | Complete
3 | Customers List[Seller] & Order Information | Phạm Tuyết Lan | Complete
4 | Products List [Sale] + Sale DashBoard | Phạm Anh Đức | Complete
5 | User List & My Orders (xem lịch sử order) (Tổng quát) | Bùi Quốc Vũ | Complete
6 | Feedback | Bùi Thái Dương | In Progress
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | 1 số thành viên khi push code lên github bị lỗi | Done | Hướng dẫn trong meet
2 |  | Done | Hướng dẫn trong meet
IV. Next Week Plan
# | Project Work Item | Time | Notes (Task Details, etc.) | Link Google Meet
1 | Continue to execute Iteration 1 & 2 |  | Each member's work will be reported every day | link
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | none
VI. Tranning
# | Project Work Item | Time | Notes (Task Details, etc.) | Memtor | Recording Link
1 | none
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C15: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue