## BackLog
THE APPLICATION DEVELOPMENT PROJECT TOPIC (SWP391)
ASSIGNMENT FUNCTION DETAILS - ONLINE SHOPPING SYSTEM
ITERATION 2 BACKLOG
Project: Online Shop
# | Feature | Function/Screen Details | Iteration | Level | LOC | In Charge | Status | Note
14 | Order Information | Buyer views the detail of 1 of his orders | literation 3 | Medium | 120 | Bùi Thái Dương | Complete
15 | Products List [Sale] | seller views and manages all products | literation 3 | Medium | 120 | Bùi Thái Dương | Complete
16 | Orders List [Sale] | Admin views list of all of orders | literation 3 | Simple | 60 | Trần Thị Tuyết Lan | Complete
17 | Order Details [Sale] | The seller can see the orders, they can approve the order or not | literation 3 | Simple | 60 | Phạm Anh Đức | Complete
18 | Feedback | User can view feedback from other customer about a product | literation 3 | Simple | 60 | Lê Thị Vân Anh | Complete
19 | Blogs List | List of all the blogs for visitor to read | literation 3 | Simple | 60 | Bùi Quốc Vũ | Complete
20 | Blog Details | Content of a blog | literation 3 | Simple | 60 | Bùi Quốc Vũ | Complete
21 | Blog Management | CRUD for Blog | literation 3 | Medium | 120 | Bùi Quốc Vũ | Complete
22 | Notification | Show news about your order, replies,... | literation 3 | Simple | 60 | Bùi Thái Dương | Complete
23 | Dashboard | Seller views Statistic of the sale of his products | literation 3 | Medium | 120 | Bùi Thái Dương | Complete
24 | About Shop | Contains information with embedded google map and current recruitment information | literation 3 | Simple | 60 | Phạm Anh Đức | Pending